## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Sprint 1 | 6 |  | 6 | 0 | 0 | 0 | 0 | 2 | 4 | To Do | 6
Seamless Ordering | 2 | Mason | 3 | 0 | 0 | 0 | 0 | 1 | 2 | Done | 3
Removing Orders when Completed | 2 | Vincent | 3 | 0 | 0 | 0 | 0 | 1 | 2 | Done | 3
Sprint 2 | 7 |  | 7 | 0 | 0 | 0 | 0 | 3 | 4 | To Do | 7
Customer Feedback | 2 | Mason | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 2
Data Analysis | 2 | Jordan | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 2
Adjusting Orders | 3 | Eli | 3 | 0 | 0 | 0 | 0 | 1 | 2 | Done | 3
TOTAL |  |  | 13 | 0 | 0 | 0 | 0 | 5 | 8 |  | 13